## Roadmap
CILT International | [20 empty] | Control version 8 - 23/1/17
Education Strategy Roadmap - Review Date -20/11/17 | [7 empty] | * | = Completed |  |  | Red font - changes from last version and key actions to do
| Strategy | Strategy | Headline Objective | Overall | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019
| Pillar | Action |  | Status | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Process | 1.1 | Providers following process
|  | 1.2 | Access to resources |  |  |  | website | CRM | [8 empty] | website (1) | CRM (2)
|  | 1.3 | Dashboard
|  | 1.4 | Education Committees
| Profile | 2.1 | Government recognition | [12 empty] | focus on S Africa/Kazakhstan
|  | 2.2 | Education Champions
|  | 2.3 | Go to' thought partner
|  | 2.4 | First choice option
| Product | 3.1 | CILT qualifications / KKA |  |  |  |  | Initial Review |  |  |  |  | UK Review | KKA Int Conv* | IESC July | KKA A Support materials (3) / Review (4)
|  | 3.2 | Online training directory | [7 empty] | Launch |  |  |  |  | Refresh (5) | Refresh (5)
|  | 3.3 | CPD and short courses
|  | 3.4 | E learning
| Professionalism | 4.1 | Local Education Plan | [9 empty] | ongoing mentoring required |  |  |  | Note linked to 9 below*
|  | 4.2 | CPD Toolbox | [13 empty] | *update (6)
|  | 4.3 | Government collaboration
|  | 4.4 | National conferences
| Pricing | 5.1 | Market value/competitor analysis | [13 empty] | *update (7)
|  | 5.2 | Income diversification |  |  |  | Wider products (6)
|  | 5.3 | 20% uplift in turnover annually | [8 empty] | review |  |  |  | review (8)
| Strategy Refresh | S1 | Initial review of monitor/strategy | [8 empty] | JH/JS | JH/JS
|  | S2 | Review Reporting on 3 yr Ed Strat | [10 empty] | Int Conv |  |  | review
|  | S2 | Revised Education Strategy | [10 empty] | Int Conv |  |  | review
|  | S3 | Revised Monitor regime
Notes
|  | (1) | Enhancing education content on CILT website / refresh
|  | (2) | Development of CRM tools for education material - working with Prolific/South India project
|  | (3) | Supporting templates and guidance to complement the KKA
|  | (4) | Commence rewrite of Certificate level etc
|  | (5) | Refresh of online training directory
|  | (6) | Development of additional CPD resources and tools - also linked to KKA requirements for membership and ongoing cpd
|  | (7) | Refresh of competitor institutes analysis
|  | (8) | Development of bespoke course offerings/consultancy advice stream
|  | (9) | Revised 3 year Education Strategy linked to wider strategic planning by CILT for growth