THE BUSINESS PLAN FOR CILT TANZANIA FOR THE YEAR 2018

- Introduction

The year 2018 has to open a new chapter for CILT Tanzania in terms of delivery of services to not only its members but to all those who desire professional implementation of core activities in the area of transport and logistics in Tanzania. In this regard CILT Tanzania has to operate in a business fashion involving costing services so as to earn income and to generate a profit as net earnings for increased performance and sustainable management. This is the basis for this critical approach.

- Objectives

  - To provide services to stakeholders in Transport and Logistics

  - To raise funds for the sustainable operation/  running of the office such as:

    - Stationeries and office supplies

    - Unlimited communication including telephone, Internet service and delivery of other hard copy mails

    - Support to other forms of networking like holding meetings, communication etc.

    - To plan and implement various other activities

- Activity Plans

  - Economic Activities

    - Design and implement 14 Training Programmes

    - Design and deliver 5 Driver Selection Procedures for Clients.

  - Advertising of the Economic Activities Planned.

Due to financial constraints, the planned activities were circulated to potential stakeholders only.

- Plan Execution

  - The activities planned were executed by:

    - Some competent members of the CILT Secretariat

    - Some competent members of the CILT Executive Committee

    - Other CILT competent members.

- Income and Expenditure

  - Total Income Expected  - Tshs. 22,100,000/=    see Appendix A

  - Total Expected Expenditure  - Tshs. 16,229,000/=   see Appendix A

  - Total Expected Take Home  - Tshs. 5,871,000/=   see Appendix A

BUSINESS PLAN FOR 2018

| NO | MONTH | ACTIVITY EXECUTED | DURATION | EXPECTED NUMBER OF PARTICIPANTS/ ACTIVITIES | EXPECTED FEES PER PARTICIPANT/ ACTIVITY | EXPECTED GROSS REVENUE | COSTS OF EXECUTION | EXPECTED NET REVENUE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | FEBRUARY | Conductors Course | 6 days | 20 | 50,000/= | 1,000,000/= | 750,000/= | 250,000/= |
|  |  | Bus Inspectors Course | 7 days | 10 | 100,000/= | 1,000,000/= | 550,000/= | 450,000/= |
| 2. | MARCH | 2.1 Fuel Control Course | 1 day | 20 | 50,000/= | 1,000,000/= | 750,000/= | 250,000/= |
| 3. | APRIL | 3.1 Capacity Building For Transport Operation Personnel | 3 days | 20 | 100,000/= | 2,000,000/= | 1,750,000/= | 250,000/= |
| 4. | MAY | 4.1 Driver Selection Assignment | 3 days | 1 | 600,000/= | 600,000/= | 400,000/= | 200,000/= |
|  |  | 4.2 Capacity Building on Defensive Driving | 3 days | 10 | 100,000/= | 1,000,000/= | 750,000/= | 250,000/= |
| 5. | JUNE | 5.1 Driver Selection Assignment | 3 days | 1 | 600,000/= | 600,000/= | 400,000/= | 200,000/= |
| 6. | JULY | 6.1 Capacity Building on Defensive Driving | 3 days | 10 | 100,000/= | 1,000,000/= | 750,000/= | 250,000/= |
|  |  | 6.2 Transport Management Information System | 10 days | 10 | 250,000/= | 2,500,000/= | 1,750,000/= | 750,000/= |
| 7. | AUGUST | 7.1 Dangerous Goods Drivers` Course | 2 days | 10 | 150,000/= | 1,500,000/= | 1,150,000/= | 350,000/= |
|  |  | 7.2 Fuel Control Course | 1 day | 10 | 50,000/= | 500,000/= | 400,000/= | 100,000/= |
| 8. | SEPTEMBER | 8.1 Materials Management Course | 5 days | 10 | 200,000/= | 2,000,000/= | 1,250,000/= | 750,000/= |
|  |  | 8.2 Driver Selection Assignment | 3 days | 1 | 600,000/= | 600,000/= | 400,000/= | 200,000/= |
|  |  | 8.3 Capacity Building Training Programme | 7 days | 11 | 100,000/= | 1,100,000/= | 729,000/= | 371,000/= |
| 9. | OCTOBER | 9.1 Motor Vehicle Mechanics | 2 days | 10 | 150,000/= | 1,500,000/= | 1,150,000/= | 350,000/= |
| 10. | NOVEMBER | 10.1 Driver Selection Assignment | 3 days | 1 | 600,000/= | 600,000/= | 400,000/= | 200,000/= |
|  |  | 10.2 Capacity Building on Defensive Driving | 3 days | 10 | 100,000/= | 1,000,000/= | 750,000/= | 250,000/= |
| 11. | DECEMBER | 11.1 Driver Selection Assignment | 3 days | 1 | 600,000/= | 600,000/= | 400,000/= | 200,000/= |
|  |  | 11.1 Capacity Building on Defensive Driving | 3 days | 10 | 100,000/= | 1,000,000/= | 750,000/= | 250,000/= |
|  |  | TOTALS | 71 days | 176 | 4,550,000/= | 22,100,000/= | 16,229,000/= | 5,871,000/= |