## Sheet1
Exchange rate |  |  | 1.3
Total forecast |  | UK agreed budget | UK planned budget | UK actual / forecast spend | Kazakstan & SME's agreed budget | Kazakstan & SME's planned budget | Kaz actual / forecast spend | Total agreed budget | Total planned budget | Total forecast spend | Notes
Time |  | 51498.525 | 51498.525 | 44785 | 51246 | 16931.2169 | 17950 | 102744.525 | 68429.7419 | 62735
Expenses |  | 1500 | 1500 | 1194.33 | 5100 | 17539.6825 | 19365 | 6600 | 19039.6825 | 20559
Others (translation, room hire |  |  |  |  | 10312.5 | 16382.0106 | 18932 | 10312.5 | 16382.0106 | 18932
Total |  | 52998.525 | 52998.525 | 45979 | 66658.5 | 50852.9101 | 56247 | 119657.025 | 103851.4351 | 102226
Tax @ 15% |  | 7724.7787 | 7724.7787 | 6717.75 |  |  |  | 7724.7787 | 7724.7787 | 6717.75
Total inc tax |  | 60723.3037 | 60723.3037 | 52697 | 66658.5 | 50852.9101 | 56247 | 127381.8037 | 111576.2138 | 108944
Risks | Risk level
- Additional Trainer (Ian Mills) | H |  |  | 5200 |  |  |  | 0 | 0 | 5200 | Included in forecastt
- Delegate expenses | L | [6 empty] | 0 | 0 | 0
- Additional 5% tax | H |  |  | 2239.25 |  |  |  | 0 | 0 | 2239.25
- Simultaneous translation | H | [5 empty] | 2100 | 0 | 0 | 2100 | Included in forecast
[8 empty] | 0 | 0 | 0
Total including risks |  | 60723.3037 | 60723.3037 | 60136.33 | 66658.5 | 50852.9101 | 58437 | 127381.8037 | 111576.2138 | 118483
Memo: OC costs in branch development |  |  |  | 5150
Notes
delegate expenses risk removed as will be covered by DAI
Ian Mills cost assumed at $4500k
10 days of OC time removed from tracker: May reduced from 10 days to 3 days; June reduced from 5 days to 2 days
OC flight costs for June left in as will be used by Ian Mills
Updated to Kaz 190426 budget; cultural programme removed